Region: NACF | BU: Operations | Launch Year: 2025 | PPE Recycling Program | RDU4 | Durham, NC, USA | Request Amount: $0.0127MM USD

CAPEX: $0.00MM
OPEX: $0.0127MM
NPV: $0.00MM
Payback Period: N/A

Date: 15-Sep-2025

## Executive Summary

The Operations team at RDU4 is requesting approval for $0.0127MM in OpEx to support the PPE Recycling Program. The total request includes equipment (bins and signage), vendor service fees, and logistics. This project aims to reduce landfill waste, enhance sustainability, and improve associate engagement by installing twenty PPE recycling bins across the site and partnering with Soles4Souls (S4S), a nonprofit organization affiliated with Zappos and Amazon, to repurpose gently used PPE such as gloves and vests.

This request was not included in the OP2 budget. The planned go-live date for this project is 30-Oct-2025. Full approval is requested by September 2025 to ensure installation and training occur before peak season.

Table 1: Initiative Request Total Project Cost Summary

| Total Cost | $0.0127MM |
| --- | --- |
| Prior Approval | N/A |
| Current Request | $0.0127MM |
| New Project Total | $0.0127MM |
| Future Request | N/A |
| Forecasted Project Total | $0.0127MM |

## Problem Statement

Currently, expired or damaged PPE such as gloves and safety vests at RDU4 are discarded into regular trash streams, contributing to increased landfill waste. On average, the site disposes of approximately one thousand vests and ten thousand pairs of gloves annually. This practice increases disposal costs and runs counter to Amazon’s long-term sustainability goals. Additionally, the lack of a recycling option reduces engagement opportunities for associates who value sustainable practices. Without a structured program, RDU4 is missing an opportunity to align with Amazon’s broader environmental initiatives.

## Proposed Solution

The proposed solution is to launch a PPE Recycling Program at RDU4 by installing twenty RecycleBoxBin Double Recycling Bins (25-gallon per bin, lightweight, with changeable label system) across the site in high-traffic areas. Collected PPE such as gloves and vests will be consolidated and shipped to Soles4Souls (S4S), a nonprofit partnered with Zappos and Amazon, to be washed, reused, and distributed to underserved communities or repurposed in warehouses. The program is projected to divert at least eighty percent of PPE waste from landfill while increasing associate engagement and contributing to Amazon’s Climate Pledge goals.

## Financial Summary and/or Other Benefits

### A. Financial

The total cost of the program is estimated at $12,731.00, which includes recycling bins, signage, service fees, freight, tax, and contingency. While the project does not generate a direct ROI or Net Present Value (NPV), it is expected to reduce landfill disposal costs by approximately $3,000 annually. This project was not included in the OP2 budget cycle but is aligned with sustainability initiatives.

### B. Other Benefits

Partnering with Soles4Souls provides significant non-financial benefits by repurposing PPE for reuse rather than disposal. Items are redistributed globally or reused domestically, supporting communities in need. The program strengthens Amazon’s sustainability commitments, enhances associate morale, and improves safety culture by ensuring PPE is responsibly retired. Additionally, it increases visibility of Amazon’s corporate social responsibility efforts both internally and externally.

## Scope

The program will be deployed exclusively at RDU4. A total of twenty RecycleBoxBin Double Recycling Bins will be placed in key site areas including entry vestibules, breakroom, inbound, outbound, and other high-traffic locations. No additional infrastructure is required. Installation will be completed within three days using vendor labor, with oversight by the RME and Safety teams. Signage and training will be provided to associates.

Table 3: Project Cost Breakdown

| Cost Driver | Description | Total Cost (USD) |
| --- | --- | --- |
| Vendor Labor | Vendor oversight and collection logistics | $6,000 |
| Equipment | 20 RecycleBoxBin units with signage | $4,231 |
| Freight | Estimated freight | $500 |
| Contingency | 10% contingency allowance | $1,000 |
| Tax | Estimated tax | $1,000 |
| Total |  | $12,731 |

## Disposal / Transfer of Existing Assets

No assets will be disposed of or transferred as part of this initiative.

## Sourcing Strategy

The team evaluated three potential vendors before selecting Soles4Souls (S4S), a nonprofit already partnered with Amazon via Zappos. S4S provides a sustainable outlet for PPE by cleaning, reusing, or redistributing collected items. Vendor Y and Vendor Z were eliminated due to higher costs and lack of redistribution programs. By leveraging the existing S4S partnership, RDU4 ensures the best value, minimized costs, and maximum impact.

## Risks & Blockers

- Low associate participation → Mitigation: Launch communication campaigns and provide visible signage.

- Improper items placed in bins (e.g., sharps) → Mitigation: Clear labeling and associate training.

- Vendor performance issues → Mitigation: Service Level Agreements (SLAs) to guarantee collection and reporting.

- Logistics delays → Mitigation: Align with existing Zappos/Amazon Soles4Souls logistics network.

## Safety

This project directly supports safety by reinforcing proper disposal of PPE. Damaged PPE will be removed from use and safely redirected for recycling or repurposing. During installation, work areas will be barricaded and scheduled during low-volume hours to minimize associate interaction. The program also builds awareness around PPE care and responsible use, thereby strengthening the overall safety culture.

## Deployment Timeline

Table 4: Deployment Timeline

| Deadline | Date | Description |
| --- | --- | --- |
| PO Issuance | 15-Sep-2025 | Intended date to cut POs |
| Project Start Date | 01-Oct-2025 | Bin/signage delivery and prep |
| Training/Testing | 20-Oct-2025 | Associate training and awareness campaign |
| Project Completion Date | 25-Oct-2025 | Bins installed and program ready |
| Benefit Realization Date | 30-Oct-2025 | PPE Recycling Program launch |

## Related or Previously Approved Projects

This project is a standalone initiative and is not a rollout of a previous pilot.

Table 5: Previously Approved Projects

| Project Title | Description | Cost $MM | Approval Date | Approval Link |
| --- | --- | --- | --- | --- |
| N/A | No related or previously approved projects | N/A | N/A | N/A |

## Stakeholder Table

Table 6: Stakeholder Table

| Stakeholder | Name |
| --- | --- |
| Project Owner #1/Requester | General Manager – RDU4 |
| Project Owner #2 | Sustainability Program Manager |
| Finance | Operations Finance Partner |
| Budget Owner | Site GM |
| RME | RME Manager – RDU4 |
| Ops Engineering | Ops Engineering Lead |
| Procurement / Supply Chain | Procurement Business Partner |
| WHS | WHS Manager – RDU4 |

# Appendices

Appendix 1 – Vendor Quote
RecycleBoxBin Double Recycling Bin – Large Capacity (25 gal. per bin), all plastic construction, lightweight, with changeable label system. Quoted cost: $111.55 per unit. Total for 20 units: $2,231.00 USD.

Appendix 2 – Soles4Souls Program Reference
Soles4Souls (S4S) is a nonprofit partnered with Zappos (an Amazon company) to collect and redistribute gently used clothing items, including PPE such as gloves and vests. Collected items are cleaned, reused in S4S warehouses, or distributed globally to underserved communities.
Link: https://www.zappos.com/kratos/c/soles-4-souls

Appendix 3 – Safety Risk Assessment
The PPE Recycling Program introduces no new equipment with moving parts or mechanical hazards. Potential risks are limited to improper disposal of sharps or hazardous items into recycling bins.
Mitigation: Clear bin labeling, associate training, and ongoing monitoring by WHS. Risk Assessment Forms (Operational Risk, ERGO Assessment) will be completed and attached in Spartan.

Appendix 4 – Deployment Images
Images of proposed bin design and signage to be uploaded as part of the CAR form submission